|  |  |
| --- | --- |
| **Date:** May 22, 2023 |   |
| **PEDS TEAM MEETING** |  |
| **Location:** Zoom Conference Call |  |

**MEMBER ATTENDANCE:**

🗹 David Paul, MD, Co-Chair, CCHS 🗹 Sarah Knavel, Bayhealth

🗹 Nancy Forsyth, Co-Chair, Beebe 🗹 Jessica Alvarez, Bayhealth

 Garrett Colmorgen, MD, Chair DPQC 🗹 Wendy McGee, Bayhealth

🗹 Kim Petrella, DPQC 🗹 Diane Hitchens, Tidal Health

 Joanna Costa, MD, Nemours 🗹 Lisa Klein, MCDRC

 Nancy Petit, MD, SF Khaleel Hussaini, DPH

🗹 David Hack, MD, SF Mawuna Gardesey

🗹 Samantha Carrier, Beebe 🗹 Pam Kelly, SF

🗹 Dara Hall, Delaware First Health 🗹 David Hack, MD, SF

🗹 Michelle Olkkola, CCHS 🗹 Kim York, Highmark

🗹 Megan Coalson, Amerihealth 🗹 Pam Layman, Bayhealth

🗹 Heather Gabriel, Tidal Health 🗹 Liz Zehner, Beebe

🗹 Anna Merrick 🗹 Shelby Coon

**FACILITATORS:**

|  |  |  |
| --- | --- | --- |
| 🗹 Dr. Nancy Forsyth🗹 Dr. David Paul |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **TOPIC** | **FINDINGS, CONCLUSIONS & RECOMMENDATIONS** | **ACTIONS**  | **STATUS** |
| I. Call to order | The meeting was called to order by Dr. Paul at 3:32p.m.  | No further action. | Resolved |
| II. ESC / LOS | To reduce Length of Stay (LOS), The Eat, Sleep, Console (ESC) model is to start at each facility. CCHS- was part of the ESC study and has operationalized this approach for the drug exposed infants. Beebe- has met and established a NOWS Task Force and is working to implement this approach. Working on integrating this into the EMR, developing parent education and other logistics. Next meeting is 5/25. SF- looking for space to do rooming in; trying to put together information to educate nursing and doctors and setting up sub-committee and training in the next month and establishing policy and working with OT to get into EPIC. Tidal Health: Met with the EPIC team, may not be able to be implemented until the Fall due to other priorities; providers on board, presently having issues with pediatric staffing and prioritizing educational needs for staff. Bayhealth: staff is on board, barriers in the NICU and rooming in but may be able to use a pediatric room, working with EPIC to integrate into EMR and developing policy and educational materials.  | On-going | On-going |
| III. Data Collection | Would like to gather data on this initiative- the number of babies with NOWS > 36 weeks; proportion babies treated and LOS.  | On-going | On-going |
| IV. QI Tools | Driver Diagrams may be helpful and will need to work with pharmacy to get PRN dose.  | On-going | On-going |
| V. Co-Chair Role | Dr. Paul has stepped down as Chair of DHMIC. His membership to DPQC and to this committee was as DHMIC chair. Dr. Paul to talk to Dr. Colmorgen, may need to step down in this role due to legislature.  |  |  |
| VI. Adjournment |  There being no further items, the meeting adjourned at 4:16p.m. | No further action | Resolved |

*Minutes prepared by JoEllen Kimmey, DPH*

**Upcoming Meetings:**

**June 26, 2023, 3:30pm-4:30pm**